## Exemplar - Phase 2
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Landing Page | Web Manager | Graphic Designer | Web Developer | Quality Assurance Tester | Content Writer | Web Designer
PHASE 2
Task/Deliverable
Design a landing page for Plant Pals | A | C | I | I | I | R
Create landing page mockup | A | C | C | I | C | R
Design image assets | I | R | I | I | I | A
Write content | A | I | I | I | R | I
Code landing page | A | I | R | I | I | I
Test landing page | A | I | C | R | I | I
Note: In this exemplar, all roles that are not Responsible, Accountable, or Consulted for certain tasks are marked as Informed. You may not need to keep all of these roles Informed about every task, so your answers may vary for Informed individuals.
Note on A2: Should this be "Execution phase?" -Elizabeth O'Hare
Note on B2: Remove only 1 task for Responsible -Cassie Maschhoff Also this doesn't match the stakeholders. Perhaps outdated? -Cassie Maschhoff